## Sheet1
Week commencing | Chairs’ to-do / milestone | Papers | Music / Performance | Art / Installations | alt.nime | Artifacts & Ideas | Doctoral Consortium | Workshops
October 2026
2026-10-05
2026-10-12 | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP | Finalize Call, Process, & Scope ASAP
2026-10-19
2026-10-26 | Publish Call | Publish Call | Publish Call | Publish Call | Publish Call | Publish Call | Publish Call | Publish Call
November 2026
2026-11-02
2026-11-09 |  | CMT past conferences reviewers review
2026-11-16
2026-11-23
2026-11-30 |  | Invitation to new reviewers
December 2026
2026-12-07 | Test forms | Test forms | Test forms | Test forms | Test forms | Test forms | Test forms | Test forms
2026-12-14 | Open Submission system | Open Submission system | Open Submission system | Open Submission system
2026-12-21
2026-12-28
January 2027
2027-01-04
2027-01-11
2027-01-18 | Titles, abstracts and authors due | Submit metadata by Sunday, 24th of January AoE | Submit metadata by Sunday, 24th of January AoE | Submit metadata by Sunday, 24th of January AoE
2027-01-25 | Check metadata, conflicts, expertise. Tentative Review Assignments | Check metadata, conflicts, expertise. Tentative Review Assignments | Check metadata, conflicts, expertise. Tentative Review Assignments | Check metadata, conflicts, expertise. Tentative Review Assignments
- | Full submissions due | Submit full material by Sunday, 31st of January AoE | Submit full material by Sunday, 31st of January AoE | Submit full material by Sunday, 31st of January AoE
February 2027
2027-02-01 | Screening / desk rejection | Screen; settle desk rejections Monday 1 Feb–Friday 5 Feb | Screen; settle desk rejections Monday 1 Feb–Friday 5 Feb | Screen; settle desk rejections Monday 1 Feb–Friday 5 Feb
2027-02-08 | Send out reviews | Send out reviews | Send out reviews | Send out reviews
- | Review Period | Review Period Monday 8 Feb–Sunday 28 Feb | Review Period Monday 8 Feb–Sunday 28 Feb | Review Period Monday 8 Feb–Sunday 28 Feb
2027-02-15
2027-02-22 | Initial reviews / assessments due | Complete reviews by Sunday, 28th of February AoE | Complete reviews by Sunday, 28th of February AoE | Complete reviews by Sunday, 28th of February AoE
March 2027
2027-03-01 | Discussion and paper meta-reviews | Discuss; draft meta-reviews | Discuss jury assessments | Discuss jury assessments
2027-03-08
2027-03-15 | Final reviews and meta-reviews due | Final reviews + meta-reviews by Sunday, 21st of March AoE | Final assessments by Sunday, 21st of March AoE | Final assessments by Sunday, 21st of March AoE
2027-03-22 | Chair decisions and consistency checks | Prepare decisions; check consistency Monday 22 Mar–Friday 26 Mar | Prepare decisions; check consistency Monday 22 Mar–Friday 26 Mar | Prepare decisions; check consistency Monday 22 Mar–Friday 26 Mar | Open Submission system | Open Submission system | Open Submission system | Open Submission system
- | Confirm committee |  |  |  | Confirm committee | Confirm committee | Confirm committee | Confirm committee
- | Release decisions | Release decisions Friday 26 Mar | Release decisions Friday 26 Mar | Release decisions Friday 26 Mar
2027-03-29 | Submissions due |  |  |  | Submit by Sunday, 4th of April AoE | Submit by Sunday, 4th of April AoE | Submit by Sunday, 4th of April AoE | Submit by Sunday, 4th of April AoE
April 2027
2027-04-05
2027-04-12
2027-04-19
2027-04-26
- | Release decisions |  |  |  | Release decisions Friday 30 Apr | Release decisions Friday 30 Apr | Release decisions Friday 30 Apr | Release decisions Friday 30 Apr
May 2027
2027-05-03 | Final materials / camera-ready and presenter registration due | Final Materials Submission Sunday 9th of May | Final Materials Submission Sunday 9th of May | Final Materials Submission Sunday 9th of May | Final Materials Submission Sunday 9th of May | Final Materials Submission Sunday 9th of May | Final Materials Submission Sunday 9th of May | Final Materials Submission Sunday 9th of May
2027-05-10 | Final document checks and presenter confirmations | Check files; confirm presenter and registration Monday 10 May–Friday 14 May | Check files; confirm presenter and registration Monday 10 May–Friday 14 May | Check files; confirm presenter and registration Monday 10 May–Friday 14 May | Check files; confirm presenter and registration Monday 10 May–Friday 14 May | Check files; confirm presenter and registration Monday 10 May–Friday 14 May | Check files; confirm presenter and registration Monday 10 May–Friday 14 May | Check files; confirm presenter and registration Monday 10 May–Friday 14 May
2027-05-17 | Hand over final material | Hand over papers to Proceedings Chairs | Hand over other material to Web or Publication Chairs as required | Hand over other material to Web or Publication Chairs as required | Hand over other material to Web or Publication Chairs as required | Hand over other material to Web or Publication Chairs as required | Hand over other material to Web or Publication Chairs as required | Hand over other material to Web or Publication Chairs as required
2027-05-24
2027-05-31 | Finalize technical requirements | Finalize technical requirements | Finalize technical requirements | Finalize technical requirements | Finalize technical requirements | Finalize technical requirements | Finalize technical requirements | Finalize technical requirements
June 2027
2027-06-07 | Programme and venue allocations finalized | Confirm programme, slots and venue allocation Monday 7 Jun | Confirm programme, slots and venue allocation Monday 7 Jun | Confirm programme, slots and venue allocation Monday 7 Jun | Confirm programme, slots and venue allocation Monday 7 Jun | Confirm programme, slots and venue allocation Monday 7 Jun | Confirm programme, slots and venue allocation Monday 7 Jun | Confirm programme, slots and venue allocation Monday 7 Jun
2027-06-14
2027-06-21 | Workshop / Consortium day | [5 empty] | Doctoral / Student Consortium Tuesday 22 Jun | Workshops Tuesday 22 Jun
- | Main conference | Paper presentations Wednesday 23 Jun–Friday 25 Jun | Music / performances Wednesday 23 Jun–Friday 25 Jun | Art / installations Wednesday 23 Jun–Friday 25 Jun | alt.nime programme Wednesday 23 Jun–Friday 25 Jun | Artifacts demos / Ideas posters Wednesday 23 Jun–Friday 25 Jun